## SNP-Systems
SN-P Systems GA Project Gantt Chart
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 6 |  |  | Plan Duration |  |  |  | Actual Start |  |  |  | % Complete |  |  |  | Actual (beyond plan) |  |  |  |  | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (IN WEEKS)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Test System Implementation | 1 | 3 | 1 | 5 | 100%
Project Feasibility Study | 2 | 2 | 2 | 2 | 100%
Study technologies which can be implemented to create an accurate and reliable program | 4 | 1 | 4 | 2 | 100%
Design structure for C# application | 4 | 2 | 5 | 2 | 20%
Application Development | 5 | 10 | 5 | 2 | 0%
Basic Generic SN-P Structure | 5 | 1 | 5 | 2 | 50%
Expanded Regex + Cryptographic nondeteministic functions | 6 | 2 |  |  | 0%
Configuration module for GAs | 8 | 1 |  |  | 0%
GA Implementation | 8 | 3 |  |  | 0%
Optimisation | 11 | 2 |  |  | 0%
Testing and validation of data | 13 | 1 |  |  | 0%
Data collection | 14 | 1 |  |  | 0%
Final Report Writing | 6 | 19 | 6 | 1 | 0%
Literature Review | 6 | 2 | 6 | 1 | 0%
Product Design | 8 | 3 |  |  | 0%
Implementation | 11 | 3 |  |  | 0%
Testing | 13 | 2 |  |  | 0%
Evaluation | 15 | 2 |  |  | 0%
Conclusion | 17 | 2 |  |  | 0%
Introduction | 19 | 1 |  |  | 0%
References & Appendices | 20 | 1 |  |  | 0%
Review & Finalisation | 21 | 4 |  |  | 0%